## Slide 1
H2020-WIDESPREAD-2014-669014 PaRaDeSEC
Review Meeting – RP2
RUDER BOSKOVIC INSTITUTE
ZAGREB – CROATIA
01-02/10/2018
Overview of the ongoing project activities, obstacles and solutions, current status, updated work and financial plan
WP4: Implementation of the structural changes at RBI
Presented by Stjepko Fazinic
Acting Head, Division of Experimental Physics

## Slide 2
Overview of the ongoing project activities, obstacles and solutions,
current status, updated work and financial plan
WP4: Implementation of the structural changes at RBI
Related to realization of Objective 4 from Part B :
To contribute to:
the realization of the Croatian smart specialisation strategies,
as well as take a leading role in institutional changes to implement ERA priorities.
It is planned for the ERA chair to take a leading role in the implementation of the structural funds project “Open scientific infrastructural platforms for innovative applications in economy and society” (O-ZIP), designed accordingly to the current national Smart Specialization Strategy, with the focus on the Advanced technologies and materials platform of O-ZIP. Further, the ERA Chair will take a leading role in the relevant components of the project “Cross-sector competence centre for advanced technologies” – applications of KET technologies.
A key component of O-ZIP, as well as a strategic orientation of RBI in general, is a series of structural changes necessary to improve its research and innovation excellence and to increase its capability to compete successfully for internationally competitive research funding including an open recruitment policy, gender balance, international peer review, improved doctoral training and open access policy to research infrastructure. This will be realized through the adoption of a series of key documents regulating the working environment at RBI. These changes are however not easy to fully implement in practice, as many of them go against the traditional manner of operation in the Croatian academic environment. The ERA chair is thus expected to contribute to the successful implementation of these changes. This will be achieved both through the direct involvement in the high impact O-ZIP project, as well as through becoming a formal advisor to the RBI director for matters concerning RBI institutional changes.

## Slide 3
From 2015 to today the whole set of key documents has been changed to regulate the following issues:
Assure open infrastructure, flexibility of space and structure
Introduce evaluation/restructuring of Labs and Divisions
Encourage applications to H2020 and other international projects
Encourage cooperation with the industry: patents, leadership positions
Add International exellence criteria for hiring and advancement
Add International projects criteria for getting leadership positions
Increase mobility of new staff/brain gain focus
Simplify administrative procedures, upgrade digitalization of internal procedures

## Slide 4
Key documents (from 2015 to today)
Statute (the present version from March 2015, changes under way)
Rules for evaluation of Laboratories (from June 2015)
Rules for office and laboratory allocation (from June 2015)
Hiring and promotion criteria (the present version from November 2015, updated version developed, approved within RBI in 2017 and now waiting approval of MZO)
Rules on External Collaborators (from March 2016)
Intellectual property bylaws (the present version from September 2016)
Rules for the work of Scientific Councill (from March 2016)
Organizational Structure (the last version from September 2017, upgrade on the way – CDSE formation)
Rules for distribution of funds provided by the Ministry of Science for dedicated science funding (from May 2017 for 2017; from April 2018 for 2018)
Usage of funds obtained through services and other activities on the ‘market’ (from February 2017)
Rules related to Sponsorships (from February 2017)
Rules for stimulations, salary supplements and overtime work (from February 2017)
The RBI development strategy for 2017-2023 (from May 2017)
Rules on mentorships and R&D activities of doctoral and postdoctoral students (from May 2017)

## Slide 5
Some ERA Chair recommendations for further actions
Some key structural changes can’t be realized for the moment due to limitations of national regulative which is still outdated and non-stimulating for research excellence. This considers not only regulative for research and education sector but also general rules in public sector and employment procedures.
Some possible improvements not affected by existing national regulative and which ERA Chair recommends to the RBI management:
Advancement rules define number of criteria required for hiring and promotion. It is recommended that researcher with outstanding results in just one of the criteria could be hired or promoted even if she/he doesn’t comply with all other criteria but comply with all national criteria.
Clearer distinction should be defined in the Statute between authorities of the RBI Director and Scientific Council. Presently large overlap in authorities exist in the current form of the Statute, which may cause undefined responsibility for key decisions or even may lead to conflict situations.
Criteria for membership in the RBI Scientific Council do not clearly mention research excellence while members of Division councils should have some demonstrated research excellence, including leadership of international projects.
Similarly to the point 3), current regulative doesn’t include explicit statement of excellence criteria for heads of divisions. Division heads are key persons for functioning of their divisions and are members of Scientific Council by definition.
In the same manner as for the points 3) and 4), there is no explicit research excellence criteria for members of the RBI Governing Board elected by the Scientific Council (SC elects 3 GB members).
Strategic documents and regulations should be periodically examined and changed to improve research environment at RBI and remove obstacles. RBI should increase efforts to improve decision making and regulation implementation processes.